## Open POA&M Items
FedRAMP® Plan of Action and Milestones (POA&M) Template
POAM ID | Controls | Weakness Name | Weakness Description | Weakness Detector Source | Weakness Source Identifier | Asset Identifier | Point of Contact | Resources Required | Overall Remediation Plan | Original Detection Date | Scheduled Completion Date | Planned Milestones | Milestone Changes | Status Date | Vendor Dependency | Last Vendor Check-in Date | Vendor Dependent Product Name | Original Risk Rating | Adjusted Risk Rating | Risk Adjustment | False Positive | Operational Requirement | Deviation Rationale | Supporting Documents | Comments | Auto-Approve | Binding Operational Directive 22-01 tracking | Binding Operational Directive 22-01 Due Date | CVE | Service Name
P001 | AC-1, AC-2 | Missing Access Control Policy | System lacks documented access control policy | ACAS | CVE-2024-1234 | server-01 | John Doe | Staff time and policy template | Document and implement access control policy | 2024-01-15 | 2024-06-30 | Milestone 1: Draft policy by 2024-03-01 Milestone 2: Implement by 2024-06-30 |  | 2024-01-20 | No |  |  | High | Moderate | Yes | No | No |  |  | This is a test comment | No |  |  | CVE-2024-1234 | Web Application
P002 | SC-7(5) | Firewall Misconfiguration | Firewall rules are overly permissive | Manual Review |  | firewall-01 | Jane Smith | Network team time | Review and tighten firewall rules | 2024-02-01 | 2024-03-15 |  |  |  | No |  |  | Moderate | Low | No | No | No |  |  |  | No |  |  |  | Network Infrastructure